## Sheet1
Item | Issued Raise | Planned Action | Person Responsible | Planned Date of Completion | Outcome
1 | There is poor ventilation in the wash up room. Staff report they “have nearly passed out” from the heat. | Extraction exhaust hood, Fair Cloth MO spoke to Stowe next week to install a power point, install a fan. Update 9/10/23 from MO has phoned Faircloth and Renyolds who look after our kitchen maintenance they have attended site and will be coming back this week to see where there is a problem with ventilation they will work with our Air conditioning service Energy Air to resolve. 23/10/12 Update: Exhaust hood has been confirmed to be working. Fans have been installed. Air conditioning working. | Maintence Officer (MO) | 23/10/2023 | Exhaust hood has been confirmed to be working. Fans have been installed. Air conditioning working.
2 | The washroom floor is always wet and slippery. (Obvious water hazard on floor) | Previous history of staff slips, Manager will make sure everyone is aware to dry the floor after washing, abrasive tile, had mats staff were tripping, will try again, change the process so that they are washing the trollies last. Update 9/10/23 from MO Non Slip Mats are being installed staff to monitor water build up after use of gernie | Chef Manager | 23/10/23 | Non Slip Mats are being installed staff to monitor water build up after use of gernie
3 | The 2 ‘hot box trolleys’ are too heavy and awkward. Require 2 person to push | Facility Manager has sent the email to General Manager Catering 5/10/23 regarding updates, in the meantime FM has advised Catering staff to have two staff to push the hot box and staff are to use the mezzanine level. | Facility Manager | 2023-11-15
4 | The freezer floor is slippery. It was described as an “ice rink”. visible ice on floor needs not slip map | Facility Manager has sent the email to General Manager Catering 5/10/23. Staff reminded to wear non slip rubber sole shoes | Facility Manager | 2023-11-15
5 | The cool room floor is slippery. Needs nonslip map. Trip hazard between cool room and kitchen | Facility Manager has sent the email to General Manager Catering 5/10/23. Staff reminded to wear non slip rubber sole shoes | Facility Manager | 2023-11-15
6 | The washroom is very noisy. Needs PPE | Disposible ear plugs will be kept next to the hair nets with signage | Maintence Officer | 2023-10-09 | Ear plugs purchased and in place along with signage.
7 | There is poor ventilation in the laundry, especially in summer. Needs larger fan to circulate air. | Stow will look at the plug and will purchase a fan on both walls, AC working and there is a window that can be opened. | Maintence Officer | 23/10/23 | Fans have been installed, A/C working
8 | There are no brakes on the green laundry trolley. | We will put brakes on, needs to have a holding capacity of 250kg. 9/10/23 Update: MO has investigated and tried to change wheels which were purchased , these did not fit our trolleys I will phone our local supplier AidaCare to see if they have the same wheels | Maintence Officer | 2023-11-15
10 | There is no first aid kit in the laundry. | Need to purchase a new one. Updated: 11/10/23 Correct first aid kit ordered. 16/10/23 Received now in place. | Maintence Officer | 2023-10-16 | first aid kit purchased and inplace.
11 | There is no eye wash in the laundry. | Should be in chemical rooms, eye wash stations , cleaners room, maintenance room with expiry dates. Updated: 11/10/23 purchased x 3 kits to place in laundry, chemical storeroom, and kitchen. 23/10/23 awaiting stock delivery | Care Manager | 2023-10-31
12 | There is no covid gown in the laundry. Management have stated that they supply this only during an outbreak. | Needs restocking, 23/10/23 awaiting stock delivery. PPE has been restocked in the laundry. | Maintence Officer | 23/10/23 | PPE has been restocked
13 | ‘Slip sling reducers’ on linen bags on not all linen bags. Staff requesting the “reducers’ are available for linen skips. | Slip Sling Reducers have been purchased for our other trolleys. Updated: 11/10/23 purchase 16 and in place. | Care Manager | 2023-10-09 | Slip Sling Reducers have been purchased for our other trolleys
15 | Staff report that difficulty in holding heavy doors open while moving trolleys etc through doorway. Door ‘chocks’ have been provided. | Contact Chubb for a price for a magnet. Update 9/10/23 from MO Door chocks have been provided , Wormald are costing installing magnets on both laundry doors. | Maintence Officer | 2023-11-15
16 | There are items on the floor in the oxygen storage room. | Rubbish build up, Facility Manager discuss with the RNS at handover and RN meeting. These items have been stored in correct places , more shelving needs to be purchased, will be checked on a weekly basis All staff being aware with store rooms and how they must be left. | Facility Manager/ Maintence Officer | 2023-10-19 | Floor cleared from clutter.
17 | Hot water caution signs are not near hot water taps. Management have stated that there is a safety switch on these taps. | Require signs. Updated: 11/10/23 purchased x 1 pack which includes 6 signs for each hot water zip tap. 16/10/23 signs have arrived and installed. | Maintence Officer | 2023-11-17 | Signs in place
18 | Catering assistant has stated that she regularly does not get lunch break due to workload issues in Wing 2. Management have stated that they always encourage staff to have their breaks. | Facility Manager has discussed with staff member also Chef Manager has remind staff to take their breaks and has been included in duty statements. | Facility Manager | 23/10/23 | Facility Manager has discussed with staff member also Chef Manager has remind staff to take their breaks and has been included in duty statements.
19 | There is a broken keypad ( currently is locked with key) on a door which stores a first aid kit. | This room is restricted access, only accessible by a key be authorised personnel. The first aid kits are now in the Nurses station and accessible by all staff. | Maintence Officer | 2023-10-09 | First Aid kits have been removed and placed into RN stations. The doors are only accessible by key and are not broken
20 | There are items on the floor in the communications room. | Communication room is restricted access only for IT and maintenance staff | Facility Manager | 23/10/23 | Floor is clear for authorised staff to access.
21 | There was noticeably a high level of dust in the covid floor fire stairs. | Stairwells are dusty, to be cleaned by the cleaners. | Maintence Officer | 2023-10-09 | Stairwells have been vaccumed by cleaning staff, this will be attended regularly
22 | Kitchen staff would like duties statements as staff feel stress from not being clear on their role. Management stated that they do not supply them. Only position descriptions. | Catering Manager has completed new duty statement, send to Facility Manager who has reviewed and sent out to staff for input and suggestions | Chef Manager | 2023-11-15